ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Kosovo*

## Contracting authority

Center for Counseling, Social Service and Research - SIT

## Country background

Decade ago, EU facilitated dialogue started for normalization of Serbia – Kosovo* relations, while aspired goal remains elusive. The war in Ukraine, additionally increased tension between pro-Russian and pro-Western Balkan nations, even though both IPA beneficiaries indicate devotion to the EU integration. Witnessing status quo and even derogation of neighbourly relations, socio-economic normalization is seen as one of the starting points where both sides could see their common interests. In Kosovo, youth make 53% of total population, while in Serbia they make 1/6 of total population. However, due to unsatisfied life quality, political situation and socio-economic development, young people, both in Kosovo and Serbia, strive to leave – putting the risk on socio-economic growth of both IPA economies (Serbia around 50% of young people want to leave the country, while in Kosovo this number reach 78%). The worrying fact is that only 45% of young people in Serbia support the idea of a lasting peace with Kosovo. It is estimated that new generations is by far the most belligerent in its attitudes as a consequence of the fact that the public space, educational system and the media become toxic. They never had an opportunity to gain positive formative experience of meeting the “other side” or realise that their peers face similar or same developmental challenges while stepping toward adulthood. With the fact that both Serbia and Kosovo hold similar cultural background, patriarchal gender patterns are predominant. Discriminatory stereotypes regarding the roles and responsibilities of women and men in the family and in society persist. Serbia has made an increase of 5.6 points compared to 2016, according to Gender Equality Index (2021), indicating that if it is continued at the current pace, Serbia may achieve full gender equality in 59 years. CPIA gender equality rating (1=low to 6=high) in Kosovo was reported at 3.5 in 2020 (World Bank collection of development indicators). However, gender inequality is much higher in closed, rural and deprived communities. Due to limited access to resources, services and opportunities for personal development (e.g. access to digitalization, healthcare, non-formal education), multiple forms of discrimination and even stronger patriarchal and gender norms particularly young women face with additional challenges compering to their peers of mainstream population. Young women are still more likely to drop out from basic education and often hold negative experiences with social institutions. To achieve equity, it is important to work both with young man and women. If looking at the long-term changes, investing in young people as generation that shape future is seen as priority.

## Current situation in the sector

Youth work CSOs as professionals working with youth that facilitate young people’s development, addressing gender inequalities and creating opportunities for testing values, intercultural dialogue, and „eye-opening“ experiences, are seen as another significant group when referring to building professional cross-border network focused on youth development, good neighbourly relations and transfer of know-how. When it comes to youth work professionalisation, Serbia is ahead of Kosovo with recognized youth work vocation, quality standards, National Association of Youth Workers. So, transfer of methods of good practice of addressing gender inequalities with vulnerable young man and women are subject of this Action, which will go in both directions. CZOR hold 20 years’ experience in implementing youth work formal education in partnership with Jonkoping University, Sweden. With such a capacity, CZOR developed and successfully implements program called „Mobile Youth Club“ for social inclusion of marginalised young man and women by using street, outreach and mobile youth work. On the other hand, SIT as a member of network „Be a man club“ holds significant expertise in addressing gender norms, gender equality in working with young man and women. The Action represents both piloting and scaling of the innovative approach that will merge expertise of CZOR, Serbia and SIT, Kosovo with aim to invest into innovative method to address gender equality by using street, outreach and mobile youth work as well as holistic and multidimensional approach to empowerment of young man and women. Despite existing efforts for social inclusions and gender equality targeting vulnerable young man and women in deprived communities, greatest challenge emphasised by CSOs and government in Serbia and Kosovo is outreaching. Governments points out lack of capacities for field work, while according to the research conducted by the CZOR (2020), only 11% of the CSOs in Serbia are conducting outreach activities.

## Related programmes and other donor activities

N/A

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

Providing overall assessment of impact and effectiveness of outreach gender mobile youth club methodology in Kosovo*.

## Specific objective(s)

The specific objective (Outcome) of this contract is:

To provide final external evaluation effectiveness of outreach gender mobile youth club methodology in Kosovo*.

## Expected outputs to be achieved by the contractor

Output 1. Designed and facilitated regional evaluation event for gathering necessary data for final evaluation report and assisting partners in creating relevant internal evaluation.

Output 2. Created final evaluation report focusing on:

1) Relevance of the Action for strengthening CSO professional groups from Serbia and Kosovo* to be effective and accountable independent actors, able to engage young man and women from the region in creating good neighbourhood relations;

2) Relevance and quality of the innovative youth work outreach methodology on addressing gender equality with young man and woman from the most underdeveloped areas;

3) Relevance of the action for creating possibilities for young people from the most underdeveloped urban and rural areas in Serbia and Kosovo*  for pro-active approach in addressing gender roles, norms, gender equality and other youth related themes at all community levels.

All the content shall be created in English language. During the contract selected Contractor will need to cooperate with the Contractor from Kosovo*.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

It is assumed that the Contracting Authority will provide all necessary information to the Contractor on the project documents and procedures to follow during the assignment.

It is assumed that CSOs in the region are interested to participate in all evaluation phases.

It is assumed that the expertise of the selected Contractor as well as its experience in working within relevant field will contribute to implementing projects activities and ideas in most suitable way.

## Risks

Unstable political situation due to Serbia and Kosovo* relations could reflect smooth implementation of the Action when it comes to cross-border cooperation and regional events, especially in relation to mobility (traveling).

A lack of interest and motivation of target groups, especially youth, to participate in the evaluation.

# SCOPE OF THE WORK

## General

### Description of the assignment

The project „Poke the bubble” – Gender mobile youth clubs for the new good neighbourly social initiatives between Serbia and Kosovo* aims to invest into innovative method to address gender equality by using street, outreach and mobile youth work as well as holistic and multidimensional approach to empowerment of young man and women. In order to gain those skills and increase ability for regional cooperation, CSO professionals and young man and women from underdeveloped areas are being trained and mentored to implement Gender mobile youth work methodology and to design and promote content about gender equality on social media.

The purpose of this contract is to design and conduct external and independent final evaluation of the action on the target groups and stakeholders. Moreover, the evaluation will assess the extent to which the objectives and expected results were achieved. The project performance during the implementation will also be evaluated. It is expected that best practices are drawn from the design, implementation, and monitoring mechanisms as well as internal evaluation of the project and recommendations provided regarding the sustainability of the action. The evaluator will develop a detailed methodology for the external evaluation, which will highlight aspects such as the research design, ethical considerations, sampling strategy and data collection in the targeted areas of the project including tools to be used, as well as a strategy in which both primary and secondary data will be analyzed.

The final reports from final evaluation will comprise of both quantitative and qualitative data, which shall reflect the action’s progress in achieving its targets, objectives and desired impact. Also, external evaluation of the action will contain recommendation for multiplication of the model beyond the Action. Results of the final evaluation will be used for improvement of the Model representing the base for the follow up activities, multiplication and sustainability.

### Geographical area to be covered

Kosovo* and Serbia in cooperation with the Contractor from Kosovo*

### Target groups

- Civil society organizations (CSOs) - Representatives of CSO professional groups from Kosovo* and Serbia participating in networking initiatives and capacity building.

- Youth from underdeveloped areas - Young man and women reached by programme activities, youth public actions and by Mobile youth club activities.

- Government institutions and government representatives active in the field of youth support. At least 2 government institutions and government representatives should be reached within the evaluation processes.

## Specific work

| Type of the activity | Description of the activity | Time frame |
| --- | --- | --- |
| 1. Designing evaluation methodology, evaluation methods and instruments | Detailed evaluation methodology, methods and instruments, the most suitable for achieving results defined in section 2 should be developed. The reasoning behind proposed methodology, methods and instruments are also expected to be elaborate. It should be barred in mind that evaluation should be conducted through questionnaires, evaluation meetings (focus groups) and interviews with Action stakeholders and beneficiaries. Also, desktop evaluation, review of the project documents, mid-term and internal evaluation reports should be addressed. The methodology should be submitted to the approval of the Contracting Authority (CA further). | 20th September 2025 the latest |
| 2. Performing evaluation methodology and collecting data | Performing evaluation activities, in the line with proposed methodology, methods and instruments. Communication with the Action stakeholders and beneficiaries assisted by CA. The Contractor should consider offline and online performing of activities such as focus groups, interviews and similar. | 01st October 2025 – 30th March 2026 the latest |
| 3. Participation and facilitation of Regional evaluation event in Pristina | The Contractor will in cooperation with the Contractor from Kosovo* design the regional evaluation event and assist CA in facilitation of the event. The event involves 80 project participants from Kosovo* and Serbia, including youth, sub-granted CSOs and project partners. The data collected during this event Contractor will use for the final evaluation findings. | 13th -14th October 2025 |
| 3. Analysing collected data and submitting a draft evaluation report for final evaluation supporter with draft contract implementation report | Contractor is expected to analyse collected data, derive conclusions and write a draft evaluation report with findings and recommendations from conducted final evaluation. The report shall contain a sufficiently detailed description of the different aspects of final evaluation specified within this TOR. It should include: - The overview of the performed evaluation methodology with the assessment of participation of different contract target groups and achievement of contract indicators. - Evaluation findings regarding different aspects of evaluation as described above - Overview of implemented recommendations from mid-term evaluation - Lessons learned and recommendation with possibilities for multiplication of applied gender mobile youth club methodology - Any other information considered necessary to be included in the Evaluation report by Contractor The annexes to the report should include: list of participants on focus groups, interviewed stakeholders and beneficiaries, all instruments used, photos etc. The draft final evaluation report and its annexes, should be written in English language and consistent of maximum 40 pages without annexes, and should be submitted to CA in electronic version by email as given in contact details of the Contract. The draft contract implementation report, containing overview of activities implemented, difficulties encountered and mitigations measures, during performing evaluation process, should be written in Kosovan language on maximum 5 pages, and submitted to the CA in in electronic form. | 30 days after data collection is finished 31st March 2026 the latest |
| 4. Submitting the final evaluation report on performed final evaluation of the action supported by final version of contract implementation report | The Consultant is expected to submit the final evaluation report as final version with the same specifications as the draft final evaluation report, incorporating any comments received from the CA on the draft report. Final evaluation report and annexes must comply with the latest Communication and Visibility Manual for EU External Action (see https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/visibility_requirements-near_english.pdf), and should be submitted in one original and two copies. Final version of contract implementation report with the same specifications as the draft, incorporating any comments received from the CA on the draft report should be submitted to the CA in one original and two copies. The report must be provided along with the corresponding invoice. | The final evaluation report and final version of contract implementation report should be submitted no longer than 5 working days after reception of comments on the draft 31st April 2026 the latest |

## Project management

### Responsible body

The Department of Education of the Contracting Authority will be responsible for managing this contract.

### Management structure

Ardite Shkodra, the Administration and Human Resources officert, will be responsible for implementation of tasks related to this contract on behalf of the Contracting Authority.

### Facilities to be provided by the contracting authority and/or other parties

Premises and working material needed for implementation of the trainings will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

Kosovo*

## Start date & period of implementation of tasks

The intended start date is 12.09.2025. and the period of implementation of the contract will be 8 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required. The Contractor will provide a sufficient number of relevant experts to deliver the services/results as indicated in this Terms of References.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

N/A

## Office accommodation

N/A

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English language in one original versions:

Draft contract implementation report of maximum 5 pages to be produced after maximum 8 months from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the report. This report should be submitted to the Contracting authority in electronic form.

Final contract implementation report with the same specifications as the draft report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on improvement of the model. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

The project coordinator will provide comments or approval of the report within 5 business days of submission from the contractor. In the absence of comments or approval by the partner country within the set deadline, the reports are deemed to be approved.

# MONITORING AND EVALUATION

## Definition of indicators

- Providing quality and timely delivery of all tasks.

- Created Methodology for Research

- Included all relevant target groups as described in this ToR

- Draft evaluation reports delivered to Contracting Authority

- Final evaluation reports delivered to Contracting Authority

- Contract implementation report delivered to the Contracting Authority

## Special requirements

N/A